## SMED Worksheet
| PathStone Group |  | SMED PROCESS WORKSHEET
Process: | Carbonation process |  |  | Responsibility: |  | Tony Lopez |  |  |  | Page : | 1 of 1
Department: | Ceramic plate line |  |  | Prepared by: |  | Ernest Young |  |  |  | Date: | 2022-11-05 13:13
Core Team: | Mattwe Path, Steven Ron, Zaida Perez | [8 empty] | Rev: | 1
Work Station |  | Process Flow | Activity |  | Cycle Time (min) | Before Improvement |  |  | Action Step | Comments
[5 empty] | Cycle Time | Internal | External | Parallel
Bagger |  | Prep | Prepare product on table |  | 4 | x |  |  | Reduce | Takes too long
Set up scale |  | set up | Set up tare weights, verify lecture and lights |  | 6 | x |  |  | Reduce |  |  | Eliminate
Test sample |  | set up | Test first run samples |  |  |  | x |  | N/A |  |  | Reduce
Verify final product |  | QA | [5 empty] | x | Eliminate |  |  | N/A
Line clearence |  | QA | Check list and Qa tech call |  |  | x |  |  | Reduce
Approve and signature |  | QA | QA takes to supervisor for approval, |  |  |  | x |  | Eliminate | Supervisors need to sign, not always around
Total |  |  |  |  | 10 | 0 | 0 | 0
Total % |  |  |  |  | 100 | 0% | 0% | 0%

## Action Plan
|  | PathStone Group |  | ACTION & IMPLEMENTATION PLAN
Process Area:
|  |  |  | Leader: |  |  |  | Start:
| Project: |  |  | Process owner: |  |  |  | Planned completion:
|  |  |  | Facilitator: |  |  |  | Today is: | 2022-11-05
| Who (Owner) | Who (Consulted) | What / Activity | Why / Reason | Assigned On: | Due Date for Completion | How / Approach | Comments | Status | Days To Completion
1 | Printing Process Room | Planning |  | Ability to maintain infeed conveyor and remove additonal labour | 2022-09-13 | 2022-09-14 | Sop change |  | Scheduled | -52
2 | CI Team | Prod managers |  | Reduce downtime | 2022-09-13 | 2022-09-23 | Kaizen project. Build initiative |  | In Progress | -43
3 | HR | HR manager |  | Reduce temporary people issues | 2022-09-13 | 2022-09-30 |  |  | Completed | DONE
4 | [8 empty] | To Do
5 | [8 empty] | To Do
6 | [8 empty] | To Do
7 | [8 empty] | To Do
8 | [8 empty] | To Do
9 | [8 empty] | To Do
10 | [8 empty] | To Do
11 | [8 empty] | To Do
12 | [8 empty] | To Do
13 | [8 empty] | To Do
14 | [8 empty] | To Do
15 | [8 empty] | To Do
16 | [8 empty] | To Do
17 | [8 empty] | To Do
18 | [8 empty] | To Do
19 | [8 empty] | To Do
20 | [8 empty] | To Do

## INFO SHEET
CHANGEOVER
PRODUCTION OF THE LAST GOOD PART |  | PRODUCTION OF THE FIRST GOOD PART