## CI Form V.2 (hidden)
CI BUSINESS CASE
[5 empty] | Process Area: | Pack 5 |  |  | Project initialization date: |  | 2022-02-16
[5 empty] | Leader: | Edgar Anaya |  |  | Project completion date: |  |  |  | Asistant:
[5 empty] | Process owner: | Eric Cowan |  |  | Revision #: |  | 2
[5 empty] | Facilitator: | Emanuel Alvez |  |  | Revision Date: |  | 2022-02-28
Take NOTES
Problem Definition
| Project Name | [5 empty] | Scope (Location, area, line, department, boundaries, etc.)
| Pack 5 Optimization - Reduced Operational Costs | [5 empty] | Pack 5 - Retail Packaging, Secondary Packaging
| Focus, Description and Scope (Follow 5W2H) | [5 empty] | Start Date |  |  | Estimated Completion Date
| This project's primary focus is to reduce the overall costs associated with Pack 5's operations while keeping quality as a priority. This will entail an investigation of Pack 5's packaging process from start to finish, scrap rate (cannabis material, packaging material), labour, throughput, and downtime. After the investigation, the team will then analyze the findings, recommend a solution that fulfill the customers requirements, as well as a implementation plan. The team will be using a Define, Measure, Analyze, Improve, Control (DMAIC) approach for this project. | [5 empty] | 2022-02-16 |  |  | 2022-03-31
[8 empty] | Problem Category |  | Problem Focus
[8 empty] | X | Quality |  | Problem solving
[8 empty] | X | Cost | X | Continuous Improvement
[8 empty] | X | Operational |  | Kaizen (Quick-Win)
[9 empty] | Safety |  | New Process
| Goal (Targets based on SMART) | [5 empty] | Expected Benefits (Described)
| Reduce labour head count and labour cost | [5 empty] | Increased profit margin per pouch (all sizes)
| Increased throughput for all SKU's in the room | [5 empty] | Optimized labour costs
| Reduced downtime | [5 empty] | Increased hourly throughput
| Reduced cannabis material scrap rate | [5 empty] | Reduced material costs per production order | [5 empty] | Follow the template to write the Focus, Description and Scope
Key Metrics involved (Consider current KPI's)
| KPI | [13 empty] | WHAT
| OEE |  | Productivity | [11 empty] | WHEN
| Eliminate/Reduce 8 Waste |  | Labour Productivity | [11 empty] | WHERE
WHY
WHO
Cause Analysis & Team
| Problem Symptoms (Attach initial insights) | [5 empty] | Team member |  | Roles | [5 empty] | HOW
| Downtime Reason Code | GreenBroz | Set Up | Changeovers | Product/Material | Other | Emanuel |  | Analysis and Implementation | [5 empty] | HOW MUCH (IF KNOWN)
| Hours | 3 | 7 | 14 | 2 | 5 | Baldeep / Yegor |  | Equipment support
| Product Size | 3.5g | 7.0g | 14.0g | 28.0g | WeedWallet | Eric & Natasha |  | Crew and operators
| Throughput Rate | 1457 | 982 | 800 | 700 | TBD | Cedric |  | Planning
| Labour Allocation |  | Number of People | Operation 10 | Operation 20 | Total Cost/Hr | Sona |  | Quality assurance
| Hourly Wage | 20 |  | 16 | 8 | 480 | Potential Project Risks (High costs, safety concerns, labour skills, long timeframe, lack of installations) | [5 empty] | Define the GOALS based on SMART
| - Investigate changeover proceedures: Partial Cleans (15 mins), Deep Cleans (30 mins) - Downtime reporting: Speculation that the numbers submitted for downtime is inaccurate and is causing the OEE to be skewed (10 mins changeovers reported on the shift report for deep cleans) - Repack proceedure: Several repacks leaving the room are not being entered into the system accurately which is now impacting inventory, warehouse, and planning teams - Wasted movements: Optimize room layout to minimize movement for the dynamic staff (restriction: Greenbroz) - 5s - Investigate the feasability of using the Greenbroz for large flower packaging: 28g = 4 batches , 14g = 2 batches | [5 empty] | Risk |  | Description
[7 empty] | Lack of control after implementation |  | Initiatives are not being followed post implementation
Planned Orders
Plan and Expectations
Implementation Plan (Follow 3W's)
| WHAT |  |  |  | WHO |  | WHEN |  | HOW
| Current SWI + relevant data captured and anayzed |  |  |  | CI |  | 2022-03-02 |  | SWI "as-is", analyzed, downtime reports, OEE
| Identify waste / opportunities and prioritize |  |  |  | CI |  | 2022-03-04 |  | Scrap, Motion, Waiting -> quantify impacts
| Pilot test improvements completed |  |  |  | CI |  | 2022-03-23 |  | PR runs, + changeover test/timing. + scrap controls
| Verify and complete Standards / SWI / Procedures |  |  |  | CI, Eric |  | 2022-03-28 |  | Review, update documents, get buy-ins, Metrics "to-be" |  |  |  | Follow the Improvent roadmap | Zoom it if needed
| Hand-off to process owner |  |  |  | CI, Eric |  | 2022-03-30 |  | Meeting
| Controls Required | [5 empty] | KPI's
| To-Be Process Map | [5 empty] | METRIC |  | UOM | BEFORE | AFTER | Variance %
| Training | [5 empty] | OEE |  | % |  |  | #DIV/0!
| Standard Work Instructions | [5 empty] | Throughput |  | each/hr
| SOP | [5 empty] | Downtime (Changeover) |  | Hr
| SSOP | [5 empty] | Labour Productivity |  | each/hr |  |  | #DIV/0!
| Resources Requirements | [5 empty] | Deliverables to the Process Owner (For project closure)
| RESOURCE |  | POTENTIAL ROADBLOCKS |  |  |  | SWI updated and posted
| Equipment movement |  | Probably none. Engineering is aligned |  |  |  | New targets, for Waste (scrap), optimal crew, updated in production shift reports.
Don’t forget the Guiding Principles when working in this engagement
Click here to know more about the CI Framework and Roadmap
Note on D11: What When Where Why Who How How much
Note on D19: S: Specific M: Measurable A: Attainable R: Realisitic T: Time based
Note on D25: Select or add: Productivity OEE (availability, performance, quality) Efficiency Yield Labour productivity Attainment Eliminate/Reduce 8 Waste Improve 5S

## CI Form V.3 (hidden)
CI BUSINESS CASE
[5 empty] | Process Area: | Pack 5 |  |  | Project initialization date: |  | 2022-02-16
[5 empty] | Leader: | Edgar Anaya |  |  | Project completion date: |  |  |  | Assistant:
[5 empty] | Process owner: | Eric Cowan |  |  | Revision #: |  | 3
[5 empty] | Facilitator: | Emanuel Alvez |  |  | Revision Date: |  | 2022-03-01
Take NOTES
Problem Definition
| Project Name | [5 empty] | Project Scope/Project Focus
| Pack 5 Optimization - Reduced Operational Costs | [5 empty] | In Scope: | Order fulfillment process, labour allocation, reporting, scrap rate, and downtime
| Start Date |  |  | Estimated Completion Date |  |  | Out Scope: | Process automation, machine requisition, production scheduling
| 2022-02-16 |  |  | 2022-03-31 |  |  | Problem Statement
| Project Background | [5 empty] | During the period of July 2021 to now, we have seen several cost drivers to Pack 5 and its process. First, there has been an increase in labour head from 21 to 24 people in Pack 5. This addition of labour costed $272,875 for the year (Refer to "Pack 5 Cost" for calculation) and causing an significant impact to the product cost and margin. Second, the team has faced downtime issues that have been occuring consistantly related to machines/equipments, changeovers, and set up time. Third, theres been an increase in scrap waste (cannabis and packaging material) that may be the cause of the increase in cost and material availability. All three problems do have an impact in the company's profitability and may restrict potential growth.
With Q2 underway, there have been several initiatives launched to help maintain profitability and keep expenses at a low. One of the initiatives focuses on Pack 5 and the flower packaging to challenge the current labour costs and operational costs. At current state, Pack 5 is running 5 different product sizes at different run rates using either machine filling or hand filling. The room is running 2 shifts at 9 hours with an average of 24 Dynamic staff and a PSF Supervisor. The company has seen an increase of labour head since the process design and consistent downtime causes month over month. In addition, there has been an increase in cannabis waste from April to 2022 for all 5 sizes. The cost of operation is no longer inline with the current market situation.
| Goal (Targets based on SMART) | [5 empty] | Expected Benefits (Described)
| Reduce labour to required amount | [5 empty] | Increased profit margin per pouch (all sizes)
| Maintain or increase throughput with a lower labout count | [5 empty] | Reduced labour count to 20 (both shifts) and reclaiming $272,875 in labour cost savings
| Reduce downtime duration | [5 empty] | Increased hourly throughput (if possible)
| Reduced cannabis material scrap rate | [5 empty] | Reduced material costs per production order | [5 empty] | Follow the template to write the Focus, Description and Scope
Key Metrics involved (Consider current KPI's)
| KPI | [13 empty] | WHAT
| OEE |  | Productivity | [11 empty] | WHEN
| Eliminate/Reduce 8 Waste |  | Labour Productivity | [11 empty] | WHERE
WHY
WHO
Cause Analysis & Team
| Problem Symptoms (Attach initial insights) | [5 empty] | Team member |  | Roles | [5 empty] | HOW
| Downtime Reason Code | GreenBroz | Set Up | Changeovers | Product/Material | Pouches | Emanuel |  | Analysis and Implementation | [5 empty] | HOW MUCH (IF KNOWN)
| Hours | 3 | 7 | 14 | 2 | 5 | Baldeep / Yegor |  | Equipment support
| Product Size | 3.5g | 7.0g | 14.0g | 28.0g | WeedWallet | Eric & Natasha |  | Crew and operators
| Throughput Rate | 1457 | 982 | 800 | 700 | TBD | Cedric |  | Planning
| Labour Allocation |  | Number of People | Operation 10 | Operation 20 | Total Cost/Hr | Sona |  | Quality assurance
| Hourly Wage | 20.5 |  | 16 | 8 | 492 | Potential Project Risks (High costs, safety concerns, labour skills, long timeframe, lack of installations) | [5 empty] | Define the GOALS based on SMART
| - Investigate changeover proceedures: Partial Cleans (15 mins), Deep Cleans (30 mins) - Downtime reporting: Speculation that the numbers submitted for downtime is inaccurate and is causing the OEE to be skewed (10 mins changeovers reported on the shift report for deep cleans) - Repack proceedure: Several repacks leaving the room are not being entered into the system accurately which is now impacting inventory, warehouse, and planning teams - Wasted movements: Optimize room layout to minimize movement for the dynamic staff (restriction: Greenbroz) - 5s - Investigate the feasability of using the Greenbroz for large flower packaging: 28g = 4 batches , 14g = 2 batches - Identify hot spots for waste (cannabis and packaging material) and process for reporting for waste (ACM) | [5 empty] | Risk |  | Description
[7 empty] | Lack of control after implementation |  | Initiatives are not being followed post implementation
Planned Orders
Plan and Expectations
Implementation Plan (Follow 3W's)
| WHAT |  |  |  |  | WHO | WHEN |  | HOW
| 1. DEFINE | Define customer needs and project scope |  |  |  | CI | 2022-03-03 |  | Project Charter, Kick-off Meeting, Gantt Chart; Criteria of Evaluation
| 2. MEASURE | Identify current KPI's and collect data related to the goals |  |  |  | CI | 2022-03-04 |  | Gemba, Pareto Chart, Scrap Data Collection, DPU, Yield Analysis, Process Capability/Stability
| 3. ANALYZE | Identify root causes of the problem and other potential issues |  |  |  | CI | 2022-03-23 |  | Fishbone, PFMEA, Process Mapping (Current), Spaghetti Diagram, VA/NVA Analysis,
| 4. IMPROVE | Identify top solutions for eliminating the root causes |  |  |  | CI, Eric | 2022-03-28 |  | 5s, Poka Yoke, SMED, Kanban, To Be Process Map, Cost Benefit Analysis, COE Review |  |  |  | Follow the Improvent roadmap | Zoom it if needed
| 5. CONTROL | Identify method of sustaining change |  |  |  | CI, Eric | 2022-03-30 |  | Project Handoff, Standard Work Instructions
| Controls Required | [5 empty] | KPI's
| To-Be Process Map | [5 empty] | METRIC |  | UOM | BEFORE | AFTER | Variance %
| Training | [5 empty] | OEE |  | % |  |  | #DIV/0!
| Standard Work Instructions | [5 empty] | Throughput |  | each/hr
| SOP | [5 empty] | Downtime (Changeover) |  | Hr
| SSOP | [5 empty] | Labour Productivity |  | each/hr |  |  | #DIV/0!
| Resources Requirements | [5 empty] | Deliverables to the Process Owner (For project closure)
| RESOURCE |  | POTENTIAL ROADBLOCKS |  |  |  | SWI updated and posted
| Equipment movement |  | Probably none. Engineering is aligned |  |  |  | New targets, for Waste (scrap), optimal crew, updated in production shift reports.
Don’t forget the Guiding Principles when working in this engagement
Click here to know more about the CI Framework and Roadmap
Note on D25: Select or add: Productivity OEE (availability, performance, quality) Efficiency Yield Labour productivity Attainment Eliminate/Reduce 8 Waste Improve 5S

## Kaizen Form
CI QUICK WIN INITIATIVE (KAIZEN PROJECT)
|  | PathStone Group |  | Project Title: |  |  |  | Start Date:
|  |  |  | Process Area: |  |  |  | Implementaiton date: |  |  | Assistant:
|  |  |  | Project Lead: |  |  |  | On Call Support Person:
Take NOTES
Problem Definition and Syntoms
| Problem or Improvement Opportunity Description |  |  |  |  | Project Scope/Project Focus
In Scope:
Out Scope:
| Skecth or Ilustrate the problem |  |  |  |  | Syntoms (What, where, when and how is affecting the problem)
| Key Metrics involved (What to move and how is going to be measured)) |  |  |  |  | Solving this case will help with:
WHAT
WHEN
WHY
WHO
Cause Analysis & Team
| Improvement Tools to Apply: |  |  |  |  | Financial Benefit (Ask for Support with the Calculations)
[6 empty] | Cost to Implement: |  |  |  | Total Saving:
Hard Benefits:
[6 empty] | Soft Benefits (describe): |  |  |  | anually
| Describe or Ilustrate the Analysis results |  |  |  |  | Team member | Rol and Activities to support this initiative |  |  |  |  | HOW
HOW MUCH (IF KNOWN)
Potential Project Risks (High costs, safety concerns, labour skills, long timeframe, lack of installations)
[6 empty] | Risk | Description
Implementation Plan and Results
Description of Solution (Follow 3W's)
| WHAT |  |  |  | WHO | WHEN | HOW
Describe or Ilustrate the Results
| Controls Implemented (To ensure Improvement Sustainability) |  |  |  |  | KPI's Improvmenent
| CONTROL |  | Describe how is going to support the Improvement sustainability |  |  | METRIC | UOM | BEFORE | AFTER | Improvement %
5S
QUALITY IMPROVEMENT
REDUCE "8 WASTES"
IMPROVE OPERATIONAL FLOW
IMPROVE PROCESS CONTROLS
PEOPLE PERFORMANCE
TRAINING
POKA-YOKE
SOP / SSOP / SWI
LINE BALANCING
VA/NVA ANALYSIS
PARETO / SPAGHETTI
KPI IMPLEMENTATION
FISHBONE / 5WHYs
SMED
KANBAN / PULL
SPC / CAPABILITY
COST REDUCTION

## Lists (hidden)
Process Areas | KPI's | Controls
Primary - Bucking | 8 Waste (describe) | Kanban System
Primary - Drying | Attaintment (Target) | Poke-Yoke
Primary - Sanitation | Downtime (describe) | Shift Report (with SPC)
Primary - Trimming | Labour productivity | SOP
Secondary - Edibles | OEE | SSOP
Secondary - Extraction | Productivity | Standard Work Instructions
Secondary - Label Room | Yield (waste reduction) | To-Be Process Map
Secondary - Pre rolls |  | Training
Secondary - Retail |  | Visual Control
Secondary - Tinctures |  | KPI (Production Dashboard)
Secondary - Vapes
SOP, training, audits, SPC charts, visual controls, mistake proofing, PM, etc.)